Lease Agentic Planning (LAP)

Standard Operating Procedure

| Document Version | 1.0 |
| --- | --- |
| Date | 02 May 2026 |
| Platform | Lease Agentic Planning (LAP) |
| Classification | Internal Use Only |

# 1. Purpose

This Standard Operating Procedure (SOP) describes how authorised users operate the Lease Agentic Planning (LAP) platform. LAP is an AI-powered web application that supports two core workflows for data centre lease planning projects: (1) automated IMS schedule generation from P6 PDF exports, and (2) AI-driven schedule and construction risk identification and scoring.

# 2. Scope

This SOP applies to all project team members who use LAP for:

Generating IMS baseline schedules from P6 schedule PDFs

Parsing schedule assessment Excel workbooks to identify risk candidates

Importing construction risk registers for AI-assisted risk scoring

Reviewing, editing, and exporting Acumen Fuse-compatible risk registers

# 3. Prerequisites

Before using LAP, ensure the following are in place:

## 3.1 Access

An authorised email address registered with the platform administrator.

Access to the LAP web URL (provided by the administrator).

A modern browser (Google Chrome recommended).

## 3.2 Input Files

| Module | Input File | Format |
| --- | --- | --- |
| IMS Generator | P6 Schedule Export (up to 3 projects) | .pdf |
| Schedule Risk Manager | Schedule Assessment Excel | .xlsx / .xls |
| Schedule Risk Manager | Construction Risk Register (optional) | .xlsx / .xls |

# 4. Signing In

Navigate to the LAP URL in your browser.

Enter your authorised email address in the sign-in field.

Click Sign In. If your email is not recognised, contact the platform administrator.

Upon successful sign-in, the main application loads with the left navigation sidebar visible.

Note: The session is stored in the browser. To end the session click Sign Out in the bottom-left of the sidebar. Refreshing the page while signed in will restore the session automatically.

# 5. IMS Generator

The IMS Generator reads up to three P6 schedule PDF exports in parallel and produces a structured IMS Excel workbook for each project.

## 5.1 Uploading Schedules

Click IMS Generator in the left sidebar.

Under Project 1, click Choose file and select the P6 schedule PDF.

Enter the Project Code (e.g. KUL24) and Tranche (e.g. T1).

Optionally enter an IMS Data Date and Page Range to restrict processing.

To process additional projects, click + Add Project and repeat for each slot (up to 3).

Click Convert All to start processing.

## 5.2 Reviewing Results

Each project result appears as a tab once processing completes.

Review the activity table: edit cell values inline if corrections are needed.

Click Download XLSX to download the combined IMS workbook.

Click Save to Knowledge Base to persist the result for future reference.

## 5.3 Starting a New Conversion

Click New Conversion to reset all fields and results.

# 6. Schedule Risk Manager

The Schedule Risk Manager parses a schedule assessment Excel workbook using AI (Azure OpenAI / DeepSeek) to identify, categorise, and score schedule risks. Optionally, an existing construction risk register can be uploaded so that construction risks are also extracted and included in the output.

## 6.1 Uploading Files

Click Schedule Risk Manager in the left sidebar.

Under Upload Assessment, click Choose file and select the schedule assessment Excel.

Enter the Project Code, Tranche(s) (e.g. T5-T10), and Assessment Date.

Optionally, under Upload Construction Risk Register, click Choose file and select the construction risk register Excel. The file will be sent automatically with the parse request.

Click Parse & Score Risks to start AI parsing.

## 6.2 Risk Scoring Rules

LAP uses a 1–6 numeric scale (aligned with Acumen Fuse):

| Score | Label | Description |
| --- | --- | --- |
| 1 | Negligible | Minimal likelihood or impact |
| 2 | Very Low | Low but measurable risk |
| 3 | Low | Manageable with standard controls |
| 4 | Medium | Requires active monitoring |
| 5 | High | Significant schedule threat |
| 6 | Very High | Critical — escalation required |

Schedule risks derive probability from the LPSS sheet (probability_ratio = row_score ÷ row_weight_%) and schedule impact from the criterion weight relative to the total weight. Construction risk scores are read directly from the register; missing values prompt a manual scoring step.

## 6.3 Reviewing and Editing Risks

The Risk Candidates table lists all identified risks (S-prefix = schedule, C-prefix = construction).

Click the pencil icon on any row to edit risk name, category, evidence, probability, or impact inline.

Click the expand icon (chevron) to view full evidence text for a risk.

To remove a risk from the output, click the trash icon on the row.

To add a risk manually, click + Add Risk and complete the fields in the new row.

To merge two or more similar risks, tick their checkboxes then click Merge Selected. Evidence is concatenated and the highest scores are retained.

## 6.4 Manual Scoring Modal

If any construction risk is missing probability or schedule impact scores, a scoring modal appears after parsing. Assign a 1–6 value to each risk using the dropdowns (or apply a batch score to all at once), then click Save & Close.

## 6.5 Downloading the Risk Register

Once the risk list is finalised, click Download Risk Register to export an Acumen Fuse-compatible Excel file.

Click Save to Knowledge Base to store the risk set for future AI calibration.

# 7. AI Models and Services

| Function | Service | Model |
| --- | --- | --- |
| P6 PDF extraction | Azure Document Intelligence | Layout model |
| IMS table generation | Azure OpenAI | GPT-5.4 (gpt-5.4) |
| Schedule risk parsing | Azure OpenAI / DeepSeek | DeepSeek-V4-Flash |
| Construction risk extraction | Azure OpenAI / DeepSeek | DeepSeek-V4-Flash |

# 8. Troubleshooting

| Issue | Likely Cause | Resolution |
| --- | --- | --- |
| Sign-in fails | Email not in authorised list | Contact platform administrator to add email |
| Parsing failed: 500 error | AI service timeout or malformed Excel | Check server logs; retry; verify Excel is not password-protected |
| 0 construction risks extracted | Register file is encrypted or in unsupported format | Save the file as .xlsx in Excel, remove password protection, and re-upload |
| Construction risks fewer than expected | Closed risks are filtered out by design | Only Open/Active risks are extracted; verify status column in register |
| No file picker appears | Browser focus issue on macOS | Click elsewhere on the page first, then click Choose file again |
| Results do not match expected risks | AI consolidation or category mismatch | Use + Add Risk or inline edit to correct; adjust evidence and scores manually |

# 9. Version History

| Version | Date | Summary of Changes |
| --- | --- | --- |
| 1.0 | 02 May 2026 | Initial release |